## Feuille1
	Baptiste	Benoît	Dane	Gabriel				Moyenne
GUI Application
Programmation	30	50	10	25				28,75
Application's test	8	10	1	5
Game replay	8	5	1	4,5
Test of replay	2	3	0,5	3

MCTS algorithm
MCTS general algorithm	25	30	3	7,5
Test of MCTS algorithm	6	10	0,5	3
MCTS applied to TicTacToe	3	5	1	3
Test of MCTS algorithm on TicTacToe	2	5	0,5	3
MCTS applied to Connect4	5	20	1	4,5
Test of MCTS algorithm on Connect4	3	5	0,5	3
MCTS applied to Arimaa	15	20	1	6
Test of MCTS algorithm on Arimaa versus humans	10	10	2	5
Test of MCTS algorithm on Arimaa versus other AI	10	10	0,5	3
Implement MCTS with Boost library	15	30	1	6
Test of MTCS boost	5	5	0,5	3
Implement MCTS with memory management	12	20	0,5	6
Test of MCTS with memory management	5	10	0,5	3
MCTS time test (statistics)	6	10	0,5	3
Test of MCTS time	7	20	0,5	3

Converter
Implement the converter	5	5	2	6
Test the converter	2	3	1	3

parallelization
Implement CPU parallelization	5	30	5	6
Test CPU parallelization	2	10	2	3
Implement cluster parallelization	8	30	5	6
Test cluster parallelization	5	10	2	3
Implement GPU parallelization	5	30	5	6
Test GPU parallelization	2	10	2	3
Tests on Grid5000	5	10	5	6
Tests in depart	6	5	2	4,5

Reports and presentations
Conception report first draft	30	25	20	15
Conception report last draft	5	10	5	5
HTML page	6	10	13	15
HTML page final version	3	5	2	5
Documentation	10	15	5	10
Planning assessment report first draft	20	25	20	15
Final report first draft	25	20	20	20
Planning assessment report last draft	8	7	5	5
Final report last draft	6	10	5	10
Project presentation	10	15	15	15
Creation of the CD of the application	4	10	5	7,5
Demonstration	5	10	10	7,5