## Feuille1
	Prateek(Time / In hours)					Moyenne
GUI Application
Programmation	35					8.75
Application's test	5
Game replay	3
Test of replay

MCTS algorithm
MCTS general algorithm	50
Test of MCTS algorithm	10
MCTS applied to TicTacToe	30
Test of MCTS algorithm on TicTacToe	5
MCTS applied to Connect4	20
Test of MCTS algorithm on Connect4	3
MCTS applied to Arimaa	30
Test of MCTS algorithm on Arimaa versus humans	10
Test of MCTS algorithm on Arimaa versus other AI	10
Implement MCTS with Boost library	10
Test of MTCS boost	5
Implement MCTS with memory management	15
Test of MCTS with memory management	5
MCTS time test (statistics)
Test of MCTS time

Converter
Implement the converter	35
Test the converter	5

parallelization
Implement CPU parallelization	45
Test CPU parallelization	20
Implement cluster parallelization	35
Test cluster parallelization	15
Implement GPU parallelization	30
Test GPU parallelization	10
Tests on Grid5000	12
Tests in depart	4

Reports and presentations
Conception report first draft	15
Conception report last draft	15
HTML page	15
HTML page final version	7
Documentation	8
Planning assessment report first draft	2
Final report first draft	10
Planning assessment report last draft	2
Final report last draft	15
Project presentation	7
Creation of the CD of the application	2
Demonstration	2