## Feuille1
	Baptiste	Benoît	Gabriel	Prateek	Mikaïl	Dane	final			v1
GUI Application								4
Programmation	30	50	25	35	15	10	30
Application's test	8	10	5	5	4	1	6
Game replay	8	5	4,5	3	10	1	6
Test of replay	2	3	3		2	0,5	3

MCTS algorithm								16
Test CAF on Windows	5	10	4	8	5	5	5
MCTS general algorithm	25	30	7,5	50	5	3	25
Test of MCTS algorithm	6	10	3	10	2,5	0,5	7
MCTS applied to TicTacToe	3	5	3	30	5	1	4
Test of MCTS algorithm on TicTacToe	2	5	3	5	2	0,5	3
MCTS applied to Connect4	5	20	4,5	20	5	1	12
Test of MCTS algorithm on Connect4	3	5	3	3	2	0,5	3
MCTS applied to Arimaa	15	20	6	30	7	1	15
Test of MCTS algorithm on Arimaa versus humans	10	10	5	10	3	2	10
Test of MCTS algorithm on Arimaa versus other AI	10	10	3	10	1,5	0,5	10
Implement MCTS with Boost library	15	30	6	10	5	1	12
Test of MTCS boost	5	5	3	5	1	0,5	5
Implement MCTS with memory management	12	20	6	15	5	1	14
Test of MCTS with memory management	5	10	3	5	2	0,5	5
MCTS time test (statistics)	6	10	3	5	2	0,5	5
Test of MCTS time	7	20	3	2,5	1	0,5	4

Converter								2
Implement the converter	5	5	6	35	7	2	6
Test the converter	2	3	3	5	2	1	3

parallelization								8
Implement CPU parallelization	5	30	6	45	7	5	10
Test CPU parallelization	2	10	3	20	3	2	4
Implement cluster parallelization	8	30	6	35	7	5	10
Test cluster parallelization	5	10	3	15	3	2	4
Implement GPU parallelization	5	30	6	30	8	5	10
Test GPU parallelization	2	10	3	10	3	2	4
Tests on Grid5000	5	10	6	12	2	5	7
Tests in depart	12	10	9	8	4	-2	10

Reports and presentations								12
Conception report first draft	30	25	15	15	10	20	20
Conception report last draft	5	10	5	15	4	5	6
HTML page	6	10	15	15	5	13	14
HTML page final version	3	5	5	7	3	2	5
Documentation	10	15	10	8	4	5	10
Planning assessment report first draft	20	25	15	2	7	20	20
Final report first draft	25	20	20	10	10	20	20
Planning assessment report last draft	8	7	5	2	3	5	5
Final report last draft	6	10	10	15	4	5	10
Project presentation	10	15	15	7	5	15	15
Creation of the CD of the application	4	10	7,5	2	5	5	6
Demonstration	5	10	7,5	2	2	10	8
								42