## Feuille1
				Moyenne
GUI Application
Programmation	15					3,75
Application's test	4
Game replay	10
Test of replay	2

MCTS algorithm
MCTS general algorithm	5
Test of MCTS algorithm	2,5
MCTS applied to TicTacToe	5
Test of MCTS algorithm on TicTacToe	2
MCTS applied to Connect4	5
Test of MCTS algorithm on Connect4	2
MCTS applied to Arimaa	7
Test of MCTS algorithm on Arimaa versus humans	3
Test of MCTS algorithm on Arimaa versus other AI	1,5
Implement MCTS with Boost library	5
Test of MCTS boost	1
Implement MCTS with memory management	5
Test of MCTS with memory management	2
MCTS time test (statistics)	2
Test of MCTS time	1

Converter
Implement the converter	7
Test the converter	2

parallelization
Implement CPU parallelization	7
Test CPU parallelization	3
Implement cluster parallelization	7
Test cluster parallelization	3
Implement GPU parallelization	8
Test GPU parallelization	3
Tests on Grid5000	2
Tests in depart	2

Reports and presentations
Conception report first draft	10
Conception report last draft	4
HTML page	5
HTML page final version	3
Documentation	4
Planning assessment report first draft	7
Final report first draft	10
Planning assessment report last draft	3
Final report last draft	4
Project presentation	5
Creation of the CD of the application	5
Demonstration	2